Project: Strengthening Maternal Neonatal Health Services in Partnership with the Local Government

Annual Narrative Report

Name of the Partner Organization: Snowland Integrated Development Centre

Name of the District: Humla

Reporting Period (AD): 1st Jan to 31st Dec, 2025

Name of the Reporter and Designation: Anu Rokaya ¦ Project Coordinator

Project Summary <Please provide a brief summary description of the project>

- TOT on HFOMC at District/Provincial Level: A three-day TOT on HFOMC was conducted at the district level with Health Coordinators and Sub-Health Coordinators from seven Rural Municipalities, in coordination with the Health Service Office, Humla. - HFOMC training at Health Facility: A total of 15 two-day HFOMC training events were conducted at 15 health posts (Gothi, Ripa, Madana, Maila, Melchham, Lali, Shreenagar, Kalikalauthi, Barai, Thehe, Khagalgaun, Raya, Muchu, Darma, and Dandafaya). Altogether, 106 HFOMC members were trained to strengthen governance, leadership, and accountability at the health facility level. - Comprehensive Health Profile: Comprehensive health profiles of all municipalities were prepared using available data and shared with seven Rural Municipalities of Humla district (Namkha, Simkot, Kharpunath, Sarkegad, Chankheli, Adanchuli, and Tanjakot). These profiles provide key information on municipal context and public health service utilization and will be updated continuously as new information becomes available. - Technical assistance at Palika level for annual planning and budgeting of health services (Phase 3) : A total of 16 technical assistance activities were carried out during the year at HSO Humla/District Hospital (5 events), Simkot RM (1), Kharpunath RM (2), Sarkegad RM (3), Rodikot HP (1), Rahadev BHSC (1), Chankheli RM (1), Piplang BC (1), and Adanchuli RM (1). These activities aimed to strengthen the integration of Maternal and Newborn Health (MNH) services into the annual health plans and budgets of the Rural Municipalities. - Health Planning and Budgeting Workshop: Four HPBW events were successfully conducted in Namkha, Simkot, Sarkegad, and Tanjakot Rural Municipalities. The workshops focused on health policies and MNH targets, resulting in MNH budget allocation by all participating municipalities. - Consultation meeting with local government: Three consultation meetings were conducted with Kharpunath, Sarkegad, and Chankheli Rural Municipalities. During the meetings, OHW plan progress was also shared at Kharpunath RM and Chankheli RM, and Lali and Chhipra HP (Kharpunath RM), Barai and Rodikot HP (Sarkegad RM), and Melchham and Shreemastha HP (Chankheli RM) were selected for further interventions. - One-day orientation to the local government representative, HFOMC and FCHVs on CHSB: Six one-day orientation events on CHSB were conducted for local government representatives, HFOMC members, and FCHVs at Lali and Chhipra HP (Kharpunath RM), Barai and Rodikot HP (Sarkegad RM), and Melchham and Shreemastha HP (Chankheli RM). - Conduction of health mother's group meetings using self-applied tool for quality health (SATH): A total of 24 community group discussions were conducted in 18 villages (Gopka, Lali, Pyusa, Maja, Lekha, Chhipra, Mathillo Pali, Tallo Pali, Piplang, Puma, Korka, Charigaun, Barai, Chyagi, Gyushi, Karkibada, Panimul, and Thulogaun) with 423 participants, focusing on MNH issues using the Self-Assessment Tool for Health (SATH). - Interface meeting involving HFOMC members, health workers, service users, FCHVs, representatives from CBOs, local influential leaders, and representative from local government: Six interface meetings were conducted this year at Lali, Chhipra, Melchham, Shreemastha, Barai, and Rodikot health posts. The meetings involved HFOMC members, health workers, service users, FCHVs, CBO representatives, local leaders, and local government representatives to review health facility performance. - Review meeting every six months for interface: Two interface review meetings were conducted this year at Barai and Rodikot health posts under the CHSB program. The meetings reported significant improvements in various indicators and were attended by 208 participants, including local stakeholders, HFOMC members, health workers, FCHVs, social leaders, student champions, and teachers, with more than half being female. - Orientation and mobilization of student champion on MNH focusing on the local barriers to MNH service utilization: This year, five school health programs were conducted at Shree Himalaya Secondary School (Chankheli RM), Shree Chandraprakash Secondary School (Tanjakot RM), Shree Himjyoti Model Secondary School (Sarkegad RM), Shree Laliguras Higher Secondary School (Sarkegad RM), and Sita Model Secondary School (Kharpunath RM). The programs aimed to train student champions to act as motivators, influencers, and leaders in promoting MNH service utilization by addressing local barriers. - Interaction program with pregnant, recently delivered women, caretakers, and family members to increase health-seeking behavior: The program aimed to raise awareness about maternal and neonatal health services and increase their utilization through health facilities. In 2025, a total of 20 interaction programs were conducted in 20 communities (Dulli, Sayda, Maja, Chhipra, Piplang, Yanchu, Chauganphaya, Buwa, Chautaribada Tole, Unapani, Sati, Bhandari Tole, Raya, Kankhe, Thali, Thehe, Yari, Yalbang, Gothelbada, and Dandafaya villages), with 381 pregnant women, recently delivered women, and health mothers’ group members participating. - Celebration of Days related to MNCH at local level: This program aims to raise community awareness about MNH issues and solutions in coordination with local government, health facilities, FCHVs, and health mothers’ groups. This year, three MNH-related events; Safe Motherhood Month, Breastfeeding Week, and FCHV Day were celebrated in Simkot RM in collaboration with HSO, Simkot RM, and other organizations. - MNH message broadcasting: Information and communication are key to reaching beneficiaries, stakeholders, and communities. Revised MNH messages have been broadcast to target communities through local FM radio from May onwards. - TOT on BPP/MISO at district/Palika level: In coordination with the Health Service Office, Humla, a one-day TOT on BPP/MISO was conducted at the district level with seven Rural Municipality Health Coordinators, Sub-Health Coordinators, and District Supervisors. - BPP/MISO refresher training to FCHVs and Health workers at HF: Conducted total 19 BPP/ MISO refresher training at Saya, Syada, Chhipra, Darma, Hepka, Ripa, Gothi, Jair, Melchham, Mimi, Rodikot, Shreenagar, Lali, Kalikalauthi, Barai, Raya, Madana, Maila and Kharpunath HP. The main objective of these training was to reinforce knowledge, skills and standardized practices among frontline service providers responsible for reaching pregnant women at the household and community levels. - MNH Helpline and nurse with PW/RDW: Orientation was provided to 25 health facilities, and mobile top-ups were given to 17 birthing centers in Humla district. The program’s main purpose is to provide expert consultation during complicated delivery cases at health facilities. - SBA/SHP Training: In this year, we have supported 3 Nursing staffs of Namkha, Sarkegad and Chankheli RM for SHP training in close coordination & collaboration with Rural Municipalities and Health Service Office. - ROUSG Training: ROUSG training was provided to three nursing staff from Simkot, Kharpunath, and Sarkegad Rural Municipalities to support the effective implementation of the Rural Ultrasound Program, a priority under the Safe Motherhood Program, with cost-sharing by the RMs. The training aimed to provide RUSG services to pregnant women according to protocol and to enable timely identification of conditions affecting mothers and babies. - Implant Training: We have supported 2 nursing staff for Implant training from Kharpunath and Chankheli RM. The duration of training was 8 days. Implant service is one of the long acting temporary family planning methods that is included under the basic health care package. This activity aims to support the government to ensure the availability of the implant service and family planning (FP) counselling services from the community level health care delivery service points. - Program consultative and planning meeting at district level with respective stakeholders (Hub and spoke site mapping): One district-level consultative and planning meeting was conducted with relevant stakeholders for hub and spoke site mapping, with participation from 17 participants. - Mentor Development Training: In the year 2025, we have supported 7 nursing staffs for mentor development training selected for SBMP mentor training, the training was for 8 days. They are selected according to criteria. Selected mentors were from Hub site and spoke site where are high delivery status. Developed mentors was responsible for mentoring in the hub and spoke sites as well as virtual session. - Establishment of simulation room and SBMP Program: This year, simulation rooms were established at the District Hospital, Darma HP (Chankheli RM), and Shreenagar HP (Adanchuli RM). These rooms support skill practice and simulation exercises. Short orientations on the Simulation-Based Mentorship Program (SBMP) were conducted for all service providers and stakeholders, clarifying their roles and responsibilities. The simulation rooms were then set up and handed over. - Conducted Pre-Post Assessment at Hub site: Before each monthly session, pre-assessments were conducted to evaluate mentee’s knowledge and skills on the identified modules of the Simulation-Based Mentorship Program. After completing the monthly sessions, post-assessments were conducted. Four modules, divided into Phase 1 and Phase 2, were assessed at hub sites. This year, a total of four pre- and post-assessments were conducted: Darma HP (2 events), Shreenagar HP (1 event), and District Hospital (1 event). - Conduct Monthly Session at Hub site: After completion of pre-assessment, clinical mentor will run a monthly session. One module in one session. These sessions were 2 days' session. Clinical mentor toked a lead on technical part and management mentor was supported them in management of the program in favorable environment. Only one module was facilitated in one session each month. In this year, total 7 monthly sessions were conducted at Darma HP- 3 events, DH- 2 events and Shreenagar HP-2 events. - Conduct Weekly / Bimonthly Drill at Hub site: After completion of monthly session nursing staff did bimonthly drill at hub site, skill practiced and simulation scenario session between mentees every bimonthly. They have sent log book(attendance) and kobo after every drill. In this year, total 15 drills session were conducted at three Hub site ( Darma HP-8 events, DH-2 event and Shreenagar HP-5 event). - Establish a newborn resuscitation corner at each spoke site: In this year, we have supported neonatal set to Rodikot , Saya and Jair HP of Sarkegad RM, Chhipra of Kharpunath HP, Madana and Maila HP of Tanjakot RM each spoke site to establish a newborn resuscitation practice corner for practicing a newborn resuscitation skills and simulation. - Simulation based onsite coaching and mentoring at spoke site: During this year, total 14 simulation based onsite coaching and mentoring program were conducted at 10 spoke sites ( Chhipra HP-1 event, Thehe HP- 1 event, Madana HP-2 event, Maila HP- 2 event, Jaira HP- 2 event, Rodikot HP- 2 event, Dandafaya HP- 1 event, Syada HP-1 event, Saya HP-1 event and Gothi HP- 1 event). - Weekly/Bimonthly Drill at Spoke Site: After the completion of onsite coach at spoke site the nursing staff practiced in learned topics, total 34 drill session were conducted at 8 spoke sites ( Chhipra HP-1 event, Thehe HP-4 event, Maila HP-5 event, Madana HP- 2 event, Rodikot HP- 7 event, Jair HP- 4 event, Dandafaya HP- 4 event event, Saya HP- 3 and Gothi HP- 4 event) completed in this year after frequently follow up. - Post Assessment at Spoke Site: During this year, total 4 post assessment were conducted at 4 spoke site ( Jaira, Rodikot, Maila and Madana HP) under the SBMP program. The assessments evaluated participants’ knowledge, skills, and attitudes using standardized tools like Kobo Collect, skill checklists, and surveys. The process aimed to identify competency levels, address learning gaps, and develop tailored learning plans, ultimately enhancing clinical performance and professional growth through targeted mentorship. - Support essentials equipment to Birthing Centers: We have supported essential equipment's to Birthing center after the completion of need assessments with first time MSS/QIP. Ensured the equipment's will not be duplicate in Birthing centers. Total 8 health facilities (Dandafaya HP, DH, Kharpunath BH, Saya HP, Jair HP, Darma HP, Kalikalauthi HP and Maila HP) were supported essential equipment in 2025 by OHW. The respective health facilities have recorded and maintained the equipment in their inventory/asset registers and submitted copies of the registered inventory (Dakhila) reports to OHW using the government’s standard format. - Provide portable RoUSG machines to remote birthing centers: During this year, 1 portable RUSG machines were provided to Sarkegad RM. The machines are intended to provide ultrasound services to pregnant women for early detection and timely referral of complicated cases. This intervention has improved access to early detection of abnormalities and facilitated timely referral to higher-level facilities. - Review/follow up of RUSG service: This annual activity aimed to review and assess ROUSG service utilization. This year, one review event was conducted at Sarkegad RM, covering Chankheli, Adanchuli, and Tanjakot RMs, with seven participants. - Assessment of health facilities for readiness and availability of MNCH services: Three assessments were conducted at District Hospital, Kharpunath BH, and Saya HP to evaluate readiness and availability of MNCH services. - First time MSS for health facilities: During this year, 16 first-time MSS events were conducted at Shreenagar, Syada, Dandafaya, Thehe, Jair, Maila, Madana, Mimi, Darma, Melchham, Kalikalauthi, Saya, Rodikot, Muchu, Khagalgaun and Ripa HP. This program assessed the readiness and availability of basic health care services using standardized scoring tools. MSS is conducted bi-annually, with an initial assessment followed by a six-month follow-up. The assessment helped identify existing gaps and develop action plans for improvement. MSS serves as a mirror of health facilities, reflecting the actual service delivery situation. - MSS/QIP follow up of health facilities: After six months of the first-time MSS assessment, MSS/QIP follow-up activities were conducted at five health posts (Shreenagar, Jair, Mimi, Madana and Dandafaya) to sustain service readiness and availability and to address gaps identified in the previous assessment through agreed action plans. The follow-up results showed gradual improvement in identified gaps through the joint efforts of HFOMC members and health workers. These activities were accomplished through cost-sharing with the respective rural municipalities. - Tracking of maternal deaths, validation and reporting to concerned health facilities and Palika: Maternal deaths were regularly tracked, validated, and reported to the concerned health facilities and Rural Municipalities. - Support to conduct review and planning meeting at Municipal Level: Review and planning meetings for the last fiscal year were supported in five municipalities: Namkha, Simkot, Kharpunath, Sarkegad, and Chankheli. Although the plan was to cover all municipalities, staff constraints and seasonal challenges limited full participation. During these meetings, completed activities were shared, and future implementation plans were presented. - Support to conduct annual review and planning meeting at district level (involving all Palikas): We participated in the district-level review and planning meeting organized by the Health Service Office. Health coordinators, sub-health coordinators, and one health worker from each health facility of all municipalities attended and presented their progress, while EDPs in the health sector were also invited to contribute. Refreshment costs for the event were supported through a cost-sharing approach. - Joint supportive supervision and monitoring visits with representatives of local municipalities and district stakeholders: Supervision and monitoring are continuous processes aimed at achieving the program’s set goals and objectives. As planned, joint supportive supervision and monitoring visits were conducted at Dandafaya Health Post of Simkot RM, involving representatives from the DCC, Health Service Office, respective municipal authorities and health facility staffs and HFOMC members. - Integrated Monitoring: In 2025, integrated monitoring was conducted at 13 health facilities with participation from HF in-charges, HFOMC members, and nursing staff. These events helped assess facility infrastructure, HFOMC support, and service availability. - DPAC/LPAC: The main purpose of this program was to introduce the overall project to district-level stakeholders. The DPAC meeting was conducted at the Manasharawor Hotel under the chairmanship of the DAO Chairperson. The meeting was facilitated by the Senior Program Coordinator of SCO, OHW. - OHW plan/progress sharing to municipality: During this year, OHW plan and progress sharing sessions were conducted with seven 7 RMs (Namkha, Simkot, Kharpunath, Sarkegad, Chankheli, Adanchuli and Tanjakot). - OHW plan/progress sharing with DHO/DCC: This year, three OHW plan and progress sharing sessions were conducted with DCC, HSO, and HO. The sessions provided opportunities to present program achievements, discuss ongoing activities, and align future plans with local government priorities, ensuring coordinated implementation and strengthened district-level collaboration.

Implementation Process - Were you able to accomplish the activities originally set? Were there any challenges? - Has the original implementation plan been revised? Please specify any modifications to the plan originally proposed. - Were the plan, timeline, and budget feasible and adequate? Given what you know today, what would you have done differently? - Elaborate on the working modalities to meet the objectives and the interventions. What has been your biggest learning during this phase?

- Most planned activities were completed as outlined in the DIP, except for a few, such as monthly sessions at hub sites, simulation-based onsite coaching and mentoring at spoke sites, and drill sessions at both hub and spoke sites, due to time constraints, busy schedules of nursing staff, and unavailability of mentors during implementation. - The 2025 program implementation plan was largely followed with no major changes to project design, objectives, or coverage, though minor adjustments were made to address local context, operational challenges, and emerging needs. - The plan, timeline, and budget were generally adequate, with most activities completed as scheduled. A few activities required additional funds, which were managed through prior coordination and approvals. Greater budget detail and extra buffer time could have further improved efficiency and minimized adjustments. - The project’s strategies stakeholder coordination, clear communication, timely responses, evidence-based planning, capacity building, and community engagement ensured well-organized, locally responsive, and goal-aligned implementation. - SMNHS project activities were implemented in close coordination with all Palikas through a cost-sharing approach, reinforcing government partnership and shared responsibility.

Results - What are the outcomes of your intervention? Elaborate. - How were the activities assessed/followed up during this period?

- Nursing staff capacity and confidence were enhanced through the Simulation-Based Mentorship Program. - Enhanced knowledge and accountability of HFOMC members and health staff in managing birthing center equipment, IP materials, and lifesaving drugs - Strengthened knowledge of health workers and FCHVs on danger signs during pregnancy and postpartum, and birth preparedness through BPP/MISO training - Improved ANC and PNC services delivery by health facilities. - Service utilization by pregnant and recently delivered women increased, reflecting better availability, accessibility, and quality of maternal and newborn health services. - Enhanced service readiness with higher MSS scores, showing strengthened facility capacity. - Palikas allocated budgets for MNH services, prioritizing IP materials, essential medicines, equipment, ROUSG services, training, and other MNH interventions. - Palikas committed to run ROUSG services.

Challenges/Barriers/Lessons learnt - Nursing staff faced difficulties managing time during SBMP monthly sessions and drill activities. - Health sector received lower priority from local stakeholders and RM representatives. - Aligning program activities with local government schedules posed time management challenges. - The Gen Z strike disrupted field activities. - Limited participation and time contribution from Ward Chairs, Mayors, Deputy Mayors, and CAOs during workshops. - Government officials had high expectations for support from external development partners (EDPs). - Seasonal migration of local stakeholders caused frequent changes to plans, requiring additional follow-ups. Lessons learned - Regular communication with RM representatives is crucial, particularly for effective cost-sharing. - Timely communication and coordination with relevant stakeholders are essential for implementing planned activities and addressing identified gaps. - Continuous support from local levels is needed to strengthen MNH program implementation, improve service quality, and ensure sustainability of maternal and newborn health interventions. - Regular field follow-ups and review visits help to track progress, identify implementation gaps, and provide on-site technical support for ongoing service improvement. - Coordinating with the health section before proposing birthing center equipment support makes cost-sharing arrangements easier. - Integrating the MSS/QIP approach within government health programs contributes to improved quality of care and strengthens facility-level systems. - Strong relationships with district and Palika-level stakeholders enable smoother implementation and foster local ownership. - Effective cost-sharing and joint implementation mechanisms with local governments enhance program sustainability and accountability. - SMNHS project activities implemented in close coordination with all Palikas reinforce government partnership and shared responsibility. - Regular supportive supervision and monitoring are essential to ensure effectiveness, quality, and sustained program impact.

Field Voices from beneficiaries/ stakeholders/partners:

<Action oriented quality photos/videos that is related with project work and impact, minimum two narratives with raw, high quality pictures/video> “Namaste Everyone, My name is Nara Bahadur Bhandari (Health Coordinator), Simkot RM. Thank you, SIDC and One Heart Worldwide, for HP-MSS at Syada HP. And also thanks to Syada HP for coordination with SIDC and Simkot Health Section. And it’s a great achievement for Syada HP for the consistent improvement of quality services. Now, in the upcoming future, we all work together for better improvement and to make Model HP in Humla”. Nara Bahadur Bhandari Health coordinator, Simkot RM Namaskar, everyone. Thank you, SIDC and One Heart Worldwide. I am also one of the board members of SIDC. Till now, Kharpunath RM and SIDC have worked or collaborated together for a long time. Now, for upcoming days also, we will work together. Best of luck for One Heart Worldwide for these steps in Humla. Thank you. Karna Rawal Chairperson of Kharpunath RM Thank you to SIDC and OHW for working closely with us on this important activity. I apologize for the delayed this event due to my busy schedule. Sarkegad Palika has the best HP buildings among all Palikas of Humla district, but maintenance is poor due to negligence from some health workers. HF in-charges are mainly responsible for protecting and maintaining HF assets. They must stay active and accountable for their work. This is a great platform to identify and discuss all issues of our health facilities. If gaps and problems are not shared now, it will be difficult to addressed in this budget plan. So please report every issue clearly. I will include these issues in the upcoming budget and increase funding for the health sector this fiscal year. Than Bdr Rokaya Chairman of Sarkegad RM ‘‘First of all, thank you SIDC and OHW for this important training (BPP/MISO), this training is very important for FCHVs and HWs, this training helps to save the PW, RDW and neonatal from death. This training refresh our knowledge, mainly FCHVs please read Jeevan surkashya flip chart and counsel the PW and increase the HF delivery. You all know there is high home delivery in our ward, so from today onwards, we HWs, FCHVs should work together to increase the delivery in HF.'' Mr. Jayalal Buda Sr. AHW, Melchham HP, Melchham, Chankheli RM I'm 22 years old and from Chyaghi village. There isn't a birthing center in our village, and getting healthcare at the healthcare facility was challenging. It was a community health unit in our village, and the majority of pregnant women in our community give birth at home. Traveling from our village to Barai HP takes two hours. Mr. Kampani Shahi RDW from Chyaghi village, ward no. 6, Sarkegad RM Namaskar, this 2-days HFOMC training at Shreenagar HP was very helpful for us. As the HFOMC chairperson, I learned many useful management skills and knowledge. Our ward has already allocated a budget for the health sector, and we will continue to do so in the future. Health and education are our first priorities. These two sectors are very important, and we are working on improving both. Mr. Dil Bdr. Phadera HFOMC chairperson, ward no. 3, Adanchuli RM ‘’This is my 1st pregnancy time. I have done an ANC checkup. I have planned to go to Kharpunath Community Hospital for delivery. There is no practice of going to Raya HP for delivery because to go there we have to cross the river (Karunga Khola), so if we cross the river, then the newborn child will die or it will be difficult for PW during delivery. So, whoever crosses the river for delivery, their child has died. Due to this, we are forced to go to other nearby health facilities.'' Sandipa Singh Pregnant women, Karunga village During CP Namaste everyone, first of all thank you, SIDC sir. After a long time, we received such training. I think I am the oldest FCHV present here. Before 5 to 6 years ago, this MISO Chhaki program was implemented, but due to some reason, it disappeared. This training about BPP/MISO Chhaki was very important and beneficial for us. Also, thank you, SIDC, for providing the Jeevan Surakshya flip chart. We have not received a flip chart like this before, this flip chart will help us a lot in the upcoming future. From now onwards we will utilize the flip chart to counsel PW and RDW. Jayapuri Rawal FCHV, Raya HP, Kharpunath RM Namaste everyone, this two day’s simulation based onsite coaching and mentoring program was organized by SIDC and OHW at Shreenagar HP (Hub site). We are very happy for this training. All the is ongoing, but many things are changed, like IP part, disposal of gloves, wrapping the sets. We had the opportunity to learned new and updated skill and knowledge. This training was very effective for nursing staff who engaged in birthing center. We also got detailed information about all the items needed in the birthing center (QIP). Thank you SIDC team for your teaching and proper information. Gita Bista ANM of Shreenagar HP “Thank you to the SIDC team for bringing this program to our village. Through CGD and regular counselling from nurses and FCHVs, I and my family learned the importance of safe delivery. With their support, I was referred to Surkhet Hospital on time with free ambulance services. Because of their help, my baby and I are healthy. Thank you all for supporting me and my family.” Dhankura Shahi RDW, Thulo gau, Rodikot village During CGD program “We are very happy to attend the 2-day simulation-based onsite coaching and mentoring program. Before this training, we did not know the detailed processes of PPH/Shock management, newborn resuscitation, KMC, counselling, and cervical tear repair. After the training, we learned all these procedures in detail, which improved our confidence and understanding of labour room setup and infection prevention. We are very thankful to SIDC and OHW for this valuable training.” Mrs. Durga Kumari Shahi, Sr. ANM, Rodikot HP, Sarkegad RM ''We sincerely thank SIDC and OHW for organizing the 2-day simulation-based onsite coaching and mentoring program. Before the simulation training, we lacked confidence in managing PPH, shock, KMC, newborn resuscitation, and other critical procedures; however, after the first day of training and continuing till now, our skills and confidence have improved. The regular drills were very helpful for nursing staff. We are committed to using these skills in our daily services and kindly request continued support in the future. '' Mrs. Anita Thapa ANM, Maila HP, Tanjakot RM During SBMP 2nd phase at Maila HP '' We are happy to work together with the SIDC and OHW team to improve MNH service delivery through strong coordination and shared responsibility. Before the first HP-MSS at Mimi Health Post, the delivery room condition was very poor and birthing center (BC) equipment was inadequate. After the MSS, the delivery room has improved and more BC equipment is now available. To further improve the birthing center, the HP in-charge and nursing staff should closely coordinate with the RM Health Section whenever support or equipment is required. Our commitment will not remain only on paper; the required birthing center equipment will be provided as soon as possible. '' Shiwa Shahi PHN, Chankheli RM During HP- MSS follow up at Mimi HP ''Thank you to SIDC and OHW for your strong coordination and support during the HP- MSS follow-up program. We sincerely appreciate your continued support in improving MNH services and strengthening service quality at the health post. Before HP-MSS and SIDC and OHW support, the birthing center at Madana Health Post was in very poor condition with inadequate medicines and equipment. After 5–6 months, there has been significant improvement in the birthing center. Nowadays, pregnant women and recently delivered women are receiving better and more quality services.'' Rajendra Syankhu RM health section chief, Tanjakot RM During HP –MSS follow up at Madana HP, Tanjakot RM Photo Link:https://drive.google.com/drive/folders/18qjTYIysDyuYT2D0G_rinPXWHIgmQDfn